## Email_Pratibha
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_Email_001 | Email_Us | The User query DropDownlist on the Email_us link of UK Reseller Hosting is found unable to select the related queries on the web page displaying various user queries of the application. | Detailed Description: The user clicks on the link Email us of 'UK Reseller Hosting' Hyper link. The dropdown list is found unable to select the user queries of the web page contact us displaying various user queries of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link. 3. Click on the Email us link. 4. Click on the drop down list of Your query relates to field. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to select the user queries of the web page contact us displaying various User queries on the email us Link as expected. The application displays the queries but Does not select the required query from the drop down list. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_003
DF_Email_002 | Email_Us | The Name Textfield on the Email_us link of UK Reseller Hosting is found unable to throw an error after accepting speacial character on the web page displaying User name field | Detailed Description: The user clicks on the link Email us of 'UK Reseller Hosting' Hyper link. The name field is found unable to throw an error after accepting speacial character to the web page contact us of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Email us link 4. Click on the Your name textfield and Enter the invalid name Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to throw an error after accepting speacial character in name field to the web page contact us on the Email us link as expected. The application accepts the speacial characters and does not throw an error. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_005
DF_Email_003 | Email_Us | The Name Textfield on the Email_us link of UK Reseller Hosting is found unable to throw an error after leaving the name field blank on the web page displaying Contact_us details. | Detailed Description: The user clicks on the link Email us of 'UK Reseller Hosting' Hyper link. The name field is found unable to throw an error after leaving the name field blank to the web page contact us of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Email us link 4. Click on the Your name textfield and leave the field blank Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to throw an error after leaving the name field blank on the Contact us webpage as expected. The application accepts the Null value and does not throw an error. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_006
DF_Email_004 | Email_Us | The Email Textfield on the Email_us link of UK Reseller Hosting is found unable to throw an error on the web page displaying Contact_us details. | Detailed Description: The user clicks on the link Email us of 'UK Reseller Hosting' Hyper link. The email field is found unable to throw an error after accepting wrong email to the web page contact us of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Email us link 4. Click on the Your email address textfield and enter invalid email id Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to throw an error after wrong email address on the Contact us webpage as expected. The application accepts the wrong email address and does not throw an error. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_008
DF_Email_005 | Email_Us | The subject Textfield on the Email_us link of UK Reseller Hosting is found unable to throw an error after leaving the subject field blank on the web page displaying Contact_us details. | Detailed Description: The user clicks on the link Email us of 'UK Reseller Hosting' Hyper link. The subject field is found unable to throw an error after leaving the subject field blank to the web page contact us of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk. 2. Click on the UK Reseller hosting link. 3. Click on the Email us link. 4. Click on the subject textfield and leave it blank. Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to throw an error after leaving the subject field blank on the Contact us webpage as expected. The application accepts the Null value and does not throw an error. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_012
DF_Email_006 | Email_Us | The your request/ query Textfield on the Email_us link of UK Reseller Hosting is found unable to throw an error after leaving the your request/query field blank on the web page displaying Contact_us details. | Detailed Description: The user clicks on the link Email us of 'UK Reseller Hosting' Hyper link. The your request/ query field is found unable to throw an error after leaving the your request/ query field blank to the web page contact us of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Email us link 4. Click on theYour request or query field and enter invalid subject Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to throw an error after leaving the your request/ query field blank on the Contact us webpage as expected. The application accepts the Null value and does not throw an error. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_015

## DNS_Pooja
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_Login_001 | Login_FORM | The User name Textfield on the Login Page of UK Reseller Hosting is found unable to throw an error on the web page displaying domain name dropdown of the application. | Detailed Description: The user clicks on the availability check of the contact us link of 'UK Reseller Hosting' Hyper link. The domain navigation bar is found unable to select the contact us link of the web page availability check of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Click on the textbox of username and enter the invalid username Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to select the Contact us link of the web page availability check displaying various domain name on the availability check Link as expected. The application displays the Domain name but does not select the required input from the users. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | Tc_034
DF_Login_002 | Login_FORM | The Contact_us Link on the 'All domain Prices' of the 'Domain navigation bar' link on 'UK Reseller Hosting' is found unable to Redirect to the contact_us site after Clicking on the Contact_us link. | Detailed Description: The user clicks on the availability check of the contact us link of 'UK Reseller Hosting' Hyper link. The domain navigation bar is found unable to select the contact us link of the web page availability check of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Email us link 4. Click on the Your email address textfield and enter the invalid email id Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to select the Contact us link of the web page availability check displaying various domain name on the availability check Link as expected. The application displays the Domain name but does not select the required input from the users | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | Tc_037
DF_Login_003 | Login_FORM | The Create Your Account link on the GOV.UK website link of UK reseller hosting is found unable to open a login or Sign Up page displaying Create an account. | Detailed Description: The user clicks on the availability check of the contact us link of 'UK Reseller Hosting' Hyper link. The domain navigation bar is found unable to select the contact us link of the web page availability check of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Click on the textbox of username and enter the valid username 5. Click on the textbox of password and enter the valid password 6. Click on the sign in button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to select the Contact us link of the web page availability check displaying various domain name on the availability check Link as expected. The application displays the Domain name but does not select the required input from the users. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | Tc_039

## Login_Pratibha
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_Login_001 | Login_FORM | The User name Textfield on the Login Page of UK Reseller Hosting is found unable to throw an error after entering invalid user name on the web page displaying Login Credential of the application. | Detailed Description: The user clicks on the Client Area Login bar of the 'UK Reseller Hosting' Hyper link. The User name Textfield is found unable to throw an error after entering invalid user name on the web page client area login of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Click on the textbox of username and enter the invalid username Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to throw an error after entering invalid username i.e. speacial characters and numbes on the Client Area Login page link of the web page availability check displaying various domain name on the availability check Link as expected. The application displays the Domain name but does not select the required input from the users. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | Tc_034
DF_Login_002 | Login_FORM | The Contact_us Link on the 'All domain Prices' of the 'Domain navigation bar' link on 'UK Reseller Hosting' is found unable to Redirect to the contact_us site after Clicking on the Contact_us link. | Detailed Description: The user clicks on the availability check of the contact us link of 'UK Reseller Hosting' Hyper link. The domain navigation bar is found unable to select the contact us link of the web page availability check of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Email us link 4. Click on the Your email address textfield and enter the invalid email id Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to select the Contact us link of the web page availability check displaying various domain name on the availability check Link as expected. The application displays the Domain name but does not select the required input from the users | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | Tc_037
DF_Login_003 | Login_FORM | The Create Your Account link on the GOV.UK website link of UK reseller hosting is found unable to open a login or Sign Up page displaying Create an account. | Detailed Description: The user clicks on the availability check of the contact us link of 'UK Reseller Hosting' Hyper link. The domain navigation bar is found unable to select the contact us link of the web page availability check of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Click on the textbox of username and enter the valid username 5. Click on the textbox of password and enter the valid password 6. Click on the sign in button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to select the Contact us link of the web page availability check displaying various domain name on the availability check Link as expected. The application displays the Domain name but does not select the required input from the users. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | Tc_039

## StateTransition
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_State_01 | sign_in_button | The Sign in button on the Login Page of Client Area Login is found unable to redirect to domain home page after clicking on the sign in button on the web page displaying sign in fields on the application. | Detailed Description: The user clicks on the Sign in button of the Client Area Login bar of the 'UK Reseller Hosting' Hyper link. The Sign in button is found unable to redirect on the domain home page after clicking on the sign in button on the web page client area login of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Click on the textbox of username and enter the valid username 5. Click on the textbox of password and enter the valid password 6. Click on the sign in button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to redirect to the 'domain home ' page after clicking on the sign in button on the Client Area Login page link of the web page UK reseller hosting as expected. The application stays on the same page. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_State_07
DF_State_02 | Buy_Domain_button | The Buy domain button on the ' Buy Domain ' page of the 'UK Reseller Hosting' is found unable to Redirect to the All domain page after Clicking on the Buy Domain Button. | Detailed Description: The user clicks on the Buy Domain Button of the Buy Domain page of 'UK Reseller Hosting' Hyper link. The Buy Domain button is found unable to redirect to the All domain page of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Enter valid credentials and click on sign in button 5. Click on the buy Domain button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to redirect to the all domain page of UK reseller hosting link as expected. The application is redirected to the home page. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_State_08
DF_State_03 | Pay_Button | The pay button on the ' payment mode form of the 'UK Reseller Hosting' is found unable to Redirect to the next page after Clicking on the pay button. | Detailed Description: The user clicks on the pay button of the payment mode form of 'UK Reseller Hosting' Hyper link. The pay button is found unable to redirect to the next page of the web page payment mode form of the application. Steps To reproduce the bug: 1. Open the browser and enter the URL thedemosite.co.uk 2. Click on the UK Reseller hosting link 3. Click on the Client Area Login bar 4. Enter valid credentials and click on sign in button 5. Click on the buy Domain button 6. Select Domain type 7. Click on check Availability link 8. Click on the Buy Now button 9. Click on the Proceed to Payment Link 10. Select any of the payment mode from given option as follows : credit card Debit card Net Banking PAYTM" 11.Fill all mandatory data as expected 12.Click on Pay Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to navigate to the next page of payment mode form as expected. The application stays on the same page. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_State_14
DF_State_04 | contact_us_link | The contact us link on the ' check availability page of the 'UK Reseller Hosting' is found unable to Redirect to the contact us page after Clicking on the contact us link. | Detailed Description: The user clicks on the contact us link of the check availability page of 'UK Reseller Hosting' Hyper link. The Contact us link is found unable to redirect to the contatc us page of the web page check availability of the application. Steps To reproduce the bug: 1.open the browser and enter url "thedemosite.co.uk" 2.click on "UK reseller hosting" link 3.hover mouse on domain name navigation bar" 4.click on all domain on prices 5.click on "check availability" link 6.click on " Contact us" link Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application is unable to navigate to the Contact Us page of the check availability page as expected. The application stays on the same page. | Coding | Internet Explorer | Internal Dev | P0 | High | 1.3.4 | 4 | 21/11/2018 | Neelima Padmawar | Rutuja | ACT |  | TC_State_15